## Master Plan
|  |  | Week of | 2016-09-26 | 2016-10-03 | 2016-10-10 | 2016-10-17 | 2016-10-24 | 2016-10-31 | 2016-11-07 | 2016-11-14 | 2016-11-21 | 2016-11-28
Task Name | Resource | Start | Finish
Analysis | Everyone | 2016-09-27 | 2016-10-06
Team Formation | Everyone | 2016-09-27 | 2016-09-29
Meet with Mentor | Mark/Jiankun | 2016-09-29 | 2016-09-29
Define Scope | Everyone | 2016-10-01 | 2016-10-01
Research Requirements | Adam | 2016-10-01 | 2016-10-06
Determine Business Case | Adam | 2016-10-01 | 2016-10-06
How FHIR Will be Incorporated | Dom | 2016-10-01 | 2016-10-06
Conceptual Architecture | Mark | 2016-10-01 | 2016-10-06
Gantt Chart | Arnab | 2016-10-01 | 2016-10-06
Topic Presentation | Adam | 2016-10-01 | 2016-10-06
Design | Everyone | 2016-10-07 | 2016-10-23
Design Database | Dom | 2016-10-07 | 2016-10-16
Software Design | Adam/Dom | 2016-10-07 | 2016-10-16
User Interface Design | Arnab | 2016-10-07 | 2016-10-16
Create Design Specifications | Mark | 2016-10-07 | 2016-10-16
Technical Presentation | Jiankun/Mark | 2016-10-15 | 2016-10-23
Development | Everyone | 2016-10-17 | 2016-11-28
Use Case Development | Everyone | 2016-10-17 | 2016-11-28
User Interface Development | Arnab | 2016-10-17 | 2016-11-28
Progress Report | Dom/Mark | 2016-11-12 | 2016-11-13
Testing | Everyone | 2016-11-14 | 2016-12-04
Testing Plan | Mark/Jiankun | 2016-11-14 | 2016-11-28
Perform System Testing | Jiankun/Arnab | 2016-11-14 | 2016-11-28
Document Issues Found | Jiankun/Arnab | 2016-11-14 | 2016-11-28
Correct Issues Found | Dom/Adam | 2016-11-14 | 2016-12-04
Delivery | Everyone | 2016-11-21 | 2016-12-04
Evaluate & Make Improvements | Everyone | 2016-11-21 | 2016-12-04
Final Presentation | Arnab/Mark | 2016-11-21 | 2016-12-04
Key: BLUE = Roll-up Item/Major Task; GREEN = Complete; YELLOW=Started, but not complete; RED = Not Complete | [12 empty] | As of December 3, 2016

## Use Case Detail
|  |  | Week of | 2016-10-17 | 2016-10-24 | 2016-10-31 | 2016-11-07 | 2016-11-14 | 2016-11-21 | 2016-11-28
Use Cases | Resource | Start | Finish
Use Case Development | Everyone | 2016-10-17 | 2016-11-28
Set User Preferences | Dom/Mark | 2016-10-17 | 2016-11-21
Link to Provider EMR Systems | Adam/Mark | 2016-10-17 | 2016-11-21
Get Medication Orders | Dom/Arnab | 2016-11-07 | 2016-11-21
Configure Medication Administration Schedules | Adam/Dom | 2016-11-07 | 2016-11-21
Prompt to Administer Medication | Adam/Arnab | 2016-11-14 | 2016-11-28
Confirm Medication Administration Disposition | Dom/Jiankun | 2016-11-14 | 2016-11-28
Push Adherence Info | Adam/Jiankun | 2016-11-14 | 2016-11-28
Get Demographic Info | Arnab | 2016-11-30 | 2016-12-04
Key: BLUE = Roll-up Item/Major Task; GREEN = Complete; YELLOW=Started, But Not Complete; RED = Not Started | [9 empty] | As of December 3, 2016